# 2022 ANNUAL ACTION PLAN

UPPER WEST AKIM DISTRICT ASSEMBLY

PREPARED BY THE DISTRICT PLANNING COORDINATING UNIT (D.P.C.U) – SEPT. 2021

2022 ANNUAL ACTION PLAN

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area 1: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Development of Market Infrastructure | - Renovation and operationalization of 1No. Community market | Asuaba |  |  |  |  |  | 30,000.00 |  | √ |  | DWD | DPCU, TAs, ACs, Assem. Member, UCM |
| Local Economic Dev’t | SMEs Development | - Organize quarterly District LED Committee meetings | DA Conference Hall |  |  |  |  | 8,400.00 |  |  | √ |  | DPU | DLEDC, DPCU |
|  |  | - Training of 25No. SMEs on business management skills | District-wide |  |  |  |  | 15,000.00 |  |  | √ |  | DPU | DoA, DSWCD, DPCU, DA, GEA, SME groups |
|  |  | - Facilitate access to credit facilities for 10No. registered FBOs and SMEs | District-wide |  |  |  |  | 4,000.00 |  |  | √ |  | DoA | DA, DPCU, Financial institutions, MASLOC |
|  |  | - Facilitate the establishment of 1No. financial institution | Adeiso |  |  |  |  | 3,000.00 |  |  | √ |  | DPU | DPCU, DA, TAs, |
|  |  | - Support 5No. Agro-based SMEs with Cassava and Palm oil processing machines | Aboyensu, Kumikye-Kyerenyame, Achiase, Dziko-Nkwanta, Kwapong |  |  |  |  | 30,000.00 |  | 45,000.00 | √ |  | DoA | NGO/DPs, DPU DPCU, Registered agro-SMEs |
| Focus Area 2: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agricultural Dev’t | Training and extension services Agricultural Development | - Conduct 2880 Home and Farm visits by AEAs in all farming communities to provide direct extension services to farmers & FBOs fpr dissemination and training on Good Agricultural Practices to farmers | All Communities |  |  |  |  |  |  | 17,280.00 | √ |  | DADU | RADU/UWADA |
|  |  | - Disseminate Agriculture information through radio and local information centres by AEAs and DAOs | All communities |  |  |  |  |  |  | 200.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development | Agriculture Promotion Agricultural Development | - Engagement with District Assembly on awareness creation and investment opportunities in Agriculture | District wide |  |  |  |  |  | 10,000.00 |  | √ |  | DADU | RADU/UWADA |
| Agricultural Development | Livestock and poultry Production and Development | - Conduct Quarterly Animal Health Extension (AHE) And Diseases Surveillance (Both {Passive And Active) In Livestock communities | All communities |  |  |  |  | 2,760.00 |  | 6,120.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development | Youth in Agriculture | - Sensitization of youth on youth in Agriculture programs | All communities |  |  |  |  |  |  | 10,000.00 | √ |  | YEA | RADU/UWADA/AGRIC |
| Agricultural Development (Economic Development) | Planning, Budgeting and Coordination (Agricultural Development) | - Organize one (1) RELC Planning Meeting for Sixty (60) Stakeholders in Adeiso (Ensuring 40% female participation | Adeiso |  |  |  |  |  |  | 5,000.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development (Economic Development) | Staff capacity building Agricultural Development | - Conduct 12 monthly Management and 12 Staff / Technical Appraisal Meetings | Adeiso |  |  |  |  | 1,000 |  | 4,000.00 | √ |  | DADU | RADU/UWADA |
|  |  | - Conduct TEDMAG training for technical staff in Agribusiness and Record Keeping, Agricultural Marketing Value Chain and Business planning, contract negotiation and management | Adeiso |  |  |  |  |  |  | 500.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development | Women in Agriculture Programme | - Train 2 women groups on food nutrition | All communities |  |  |  |  |  |  | 2,000.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development (Economic Development) | Statistics Monitoring and evaluation (Agricultural Development) | - Conduct quarterly monitoring and evaluation visits by DDA with DCD/DCE on Agricultural activities | All Communities |  |  |  |  |  |  | 3,000.00 | √ |  | DADU | RADU/UWADA |
|  |  | - Conduct 120 monitoring and evaluation visits on field activities and projects by DAO and PJF activities | All communities |  |  |  |  | 4,800.00 |  | 9,000.00 | √ |  | DADU | RADU/UWADA |
|  |  | - Conduct quarterly data collection surveys on agricultural statistics, crop yields and animal production in the district (SRID) | All communities |  |  |  |  | 1,000.00 |  | 2,000.00 | √ |  | DADU | RADU/UWADA |
| Agricultural Development | Agriculture Promotion | - Organize 1 District Level National Farmer’s Day Celebration | Mepom |  |  |  |  | 40,000.00 |  |  | √ |  | DoA | RADU/UWADA |
| Agricultural Development | PERD (Agricultural Development) | - Raise and distribute 30,000 improved coconut seedlings and 15,000 Palm seedling to farmers | All Communities |  |  |  |  | 30,000.00 |  |  | √ |  | DoA | RADU/UWADA |
|  |  | - Organised 4 sensitization programs for women FBOs on child labour and HIV AIDS | All Agric zones |  |  |  |  | 200.00 |  |  |  |  | DoA | DSWCD/DHS |
| Focus Area 3: Tourism and Creative Industry Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Local Economic Development (Economic Development) | Tourism promotion and development (Trade, Tourism & Industrial Development) | - Formation and inauguration of District Tourism Development Committee | UWADA |  |  |  |  |  | 2,000.00 |  | √ |  | DPU | DPCU, Management |
|  |  | - Identification and information gathering on potential tourist sites | District-wide |  |  |  |  | 5,000.00 |  |  | √ |  | DPU | DPCU, DPSC, DTDC, DA,TAs |
| SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area 1 : Formal Education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Formal Education (Social Services Delivery) | Educational Infrastructure (Education and Youth Development) | - Completion of 2No. 6-Unit Classroom Blocks, Office, Store, Staff Common Room and ICT Room with Ancilliary facility | Asuokaw Islamic Primary, Asikasu RC Basic schools |  |  |  |  | 500,000.00 |  |  |  | √ | DoE | DWD, DA, DPCU |
| Formal Education | Educational infrastructure | - Completion of 2No. 2-Unit KG Classroom Block with Ancillary Facilities | Adeiso Presby, Tiokrom |  |  |  |  | 454,605.08 |  |  |  | √ | DoE | DWD, DA, DPCU |
| Formal Education | Educational Infrastructural Development | - Completion of 3No. 3-Unit Classroom Block with Ancillary Facilities | Domponiase, Owurakesim, Asuaba |  |  |  |  | 954,000.00 |  |  |  | √ | DoE | GETFUND, DWD, DA, DPCU |
| Formal Education | Educational Infrastructural Development | - Completion of 3No. Community initiated classroom block construction | Asikasu-Aburi(1&2), Sukrong Awenfi, Asoukaw Presby |  |  |  |  | 30,000.00 |  |  |  | √ | DoE | DWD, DA |
| Formal Education | Educational Infrastructure | - Rehabilitation of 3No. Basic schools | Adu Kofi DA JHS, Asuokaw Methodist Prim., Krodua D/A. |  |  |  |  |  |  | 120,000.00 | √ |  | DoE | MP, DWD, DA, DPs, DPCU |
| Formal Education | Educational Infrastructure | - Construction of 2No. 2-units K.G. classroom blocks with ancillary facilities | Asikasu Meth. K.G., Siwnkyenmu Meth. KG. |  |  |  |  |  |  | 600,000.00 | √ |  | DoE | GETFUND, DPs, DWD, DA, ,DPCU |
| Formal Education | Educational Infrastructural Development | - Construction of 2No. 3-units classroom blocks with ancillary facilities | Kuntu, D/A, Kofi Asare JHS |  |  |  |  |  |  | 900,000.00 | √ |  | DoE | GETFUND, DPs, DWD, DA, ,DPCU |
| Formal Education | Educational Infrastructural Development | - Construction of 2No. 6-units classroom blocks with ancillary facilities | Mepom-Takorase D/A primary, Yaw Kwasi D/A |  |  |  |  |  |  | 1,100,000.00 | √ |  | DoE | GETFUND, DA DWD, DPs, DPCU |
| Formal Education | Educational Infrastructural Development | - Construction of 1No. 6-units Chamber & Hall Teachers Quarters | Nyanoah-Kwaa-Baah SHS |  |  |  |  |  |  | 450,000.00 | √ |  | DoE | MP, DWD, DA, GETFUND, DPs, DPCU |
| Formal Education | ICT Training | - Provision of 50No. Computers for basic schools | Selected schools |  |  |  |  |  |  | 50,000.00 | √ |  | DoE | GETFUND, MoC, DA, DPs, DWD, DPCU |
| Formal Education | Educational Infrastructural Development | - Provision of 100No. set of KG furniture, 500No. dual desk & mono desk and 100No. Teachers’ furniture set | Selected schools |  |  |  |  | 250,000.00 |  |  | √ |  | DoE | GETFUND, DA, DPs, DWD, DPCU |
| Formal Education | School Performance Assessment | - Conduct super mock examination for JHS 3 Students | All JHS 3 |  |  |  |  | 2,000.00 | 15,000.00 |  | √ |  | DoE | GES, DA, PARENTS |
|  |  | - Undertake monitoring of school activities on school performance | District wide |  |  |  |  | 11,000.00 | 3,000.00 |  | √ |  | DoE | DA, UNICEF |
| Formal Education | Science, Technology and Maths Promotion | - Conduct Science Practical and summit for JHS 2& 3 students | All JHS 2&3 |  |  |  |  | 1,250.00 | 11,250.00 |  | √ |  | DoE | GES, DA & PARENTS |
|  |  | - Organize STMIE Clinic for 30 students | Adeiso |  |  |  |  | 10,000.00 |  |  | √ |  | DoE | DA |
|  |  | - Organize Inter-School Quiz competition | Basic Schools & SHS |  |  |  |  | 13,000.00 |  |  | √ |  | DoE | DA |
| Formal Education | Capacity Building and Training | - Organize capacity building programmes for GES Staff | All Teachers & DEO Staff |  |  |  |  | 9,000.00 | 1,200.00 |  | √ |  | DoE | GES,DA, UNICEF |
| Social Services Delivery | Education and Youth Development | - Provide Guidance and Counselling service for students in 68 Junior High Schools and senior High schools | District Wide |  |  |  |  | 3,750.00 | 1,000.00 |  | √ |  | DoE | UNICEF, DA, DHD, DSWCD |
| Formal Education | Enrolment Drive | - Organize District level Independence Day Anniversary | Adeiso |  |  |  |  | 40,000.00 |  |  | √ |  | DoE | DA, TAs, ACS/AMs |
|  |  | - Organize My First Day at School programme | Basic Schools |  |  |  |  | 20,000.00 |  |  | √ |  | DoE | DA |
| Formal Education | Education and Youth Dev’t | - Organize Best Teacher Award Program | Adeiso |  |  |  |  | 17,000.00 | 2,000.00 |  | √ |  | DoE | DA |
| Formal Education | Education and Youth Dev’t | - Organize Sport and Cultural activities | District Wide |  |  |  |  | 12,500.00 |  |  | √ |  | DoE | DA |
|  |  | - Organize screening for hearing and seeing impairment for JHS students. |  |  |  |  |  | 2,000 | 1,000 |  |  |  | DoE | DHS/DSWCD NGO |
| Focus Area 2: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Delivery | Health Care Service Delivery | - Implement CHPS Policy at health sub-districts | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 15,000.00 |  |  |  | √ | DHS | DA, GHS |
| Health Delivery | Health Care Service Delivery | - Organize quarterly community durbars in 4 health sub-districts | Nyanoa, Okurase. Asikasu, Odumkyere-Darmang |  |  |  |  | 18,000.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery (Social Services Delivery) | Logistics and Supplies (Health Delivery) | - Procure and distribute basic health equipment and supplies | All CHPS zones |  |  |  |  | 42,000.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Procure office equipment for the Health Directorate (8 desktop and 2 laptop computers, 2 printers, 1 photocopier and 1 external hard-drive) | District Health Directorate |  |  |  |  | 67,000.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Development of Asset Register and embossment of all assets in health facilities and the DHD | District Health Directorate |  |  |  |  | 5,000.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery | Health Care Service Delivery | - Establish valid NHIS accreditation for CHPS Zones and Centres | All CHPS zones |  |  |  |  | 2,300.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery | Health delivery System Management | - Decentralize DHMT functions and empower sub-district health In-Charges | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 1,000.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Undertake performance agreement contract signing with DDHS and Health facility In-charges | All Health facilities |  |  |  |  | 500.00 |  |  | √ |  | DHS | DA |
| Health Delivery | Health delivery System Management | - Establish decentralized DHIMS Data entry systems and functionalize Monthly Data Validation Teams at all BMC levels | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang District Health Directorate |  |  |  |  | 32,300.00 |  |  |  | √ | DHS | DA, GHS |
|  |  | - Provide monthly feedback bulletins and news letters on health facilities performances | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 1,000.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery | Health delivery System Management | - Conduct Monthly DHMT meetings and performance review meetings with all BMC's and stakeholders | District Health Directorate |  |  |  |  | 25,500.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Establish health facility league table and reward system for best performing health facilities | All Health facilities |  |  |  |  | 2,000.00 |  |  | √ |  | DHS | DA |
| Health Delivery (Social Services Delivery) | Human Resource management and Capacity Building (Health Delivery) | - Organize a 2-day leadership Management training for all sub-district health facility In-charges | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 4,500.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Organize a 1 day Staff Appraisal System orientation meeting, and conduct appraisals for all health staff | District Health Directorate |  |  |  |  | 5,900.00 |  |  | √ |  | DHS | DA |
| Health Delivery | Human Resource management and Capacity Building | - Distribution/posting of health staff/workers | All Heath facilities |  |  |  |  | 500.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Organize a 3-day orientation training on Effective Data Management and DHIMS for all health staff in the facilities | District Health Directorate |  |  |  |  | 11,000.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Organize orientation training for newly posted staff, and quarterly integrated outreach training and supervision | District Health Directorate & Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 9,500.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Implement the GHS Human Resource (HR) Plans, monitor Pay Roll and HR productivity and scale up the Internet Based HR Information System (iHRIS) in the district | District Health Directorate |  |  |  |  | 1,000.00 |  |  |  | √ | DHS | DA, GHS |
| Health Delivery | HIV/AIDS Reduction and Management | - Create awareness on HIV/AIDS through health promotional activities | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 3,000.00 |  |  | √ |  | DHS | DA, GHS, GAC, DAC |
|  |  | - Organize refresher course on HIV/AIDS for community volunteers and health staff | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 2,500.00 |  |  | √ |  | DHS | DA, GHS, GAC, DAC |
| Health Delivery | HIV/AIDS Reduction and Management | - Provide testing and counseling services on HIV/AIDS in all health facilities | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 1,100.00 |  |  |  | √ | DHS | DA, GHS, GAC, DAC |
|  |  | - Monitor and supervise HIV/AIDS activities in the health centres | All Health facilities |  |  |  |  | 2,700.00 |  |  |  | √ | DHS | DA, GHS, GAC, DAC |
|  |  | - Celebration of world AIDS day with sensitization of the public. | Adeiso |  |  |  |  | 2,000.00 |  |  | √ |  | DHS | DA, GHS, GAC, DAC |
|  |  | - Organize DAC meetings and HIV/AIDS response activities | DA Conference Hall & District-wide |  |  |  |  | 8,000.00 |  |  | √ |  | HIV/ AIDS FP | DAC, DA |
| Health Delivery (Social Services Delivery) | Malaria Prevention and Immunization (Health Delivery) | - Undertake health education on malaria prevention and distribution of LLINs to all under five children and pregnant women | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 3,500.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery | Under 5 Vaccination | - Vaccination of all children under five years on vaccine preventable diseases. | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 7,643.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery | Maternal and Reproductive Health | - Vaccination of all pregnant women with TD2+ vaccines | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 4,035.00 |  |  | √ |  | DHS | DA, GHS |
| Health Delivery Social Services Delivery | Health Care Service Delivery | - Organize training on causes of mental illness for Camp leaders. | Prayer Camps across the District |  |  |  |  | 9,574.00 |  |  | √ |  | DHS | DA, GHS |
|  |  | - Undertake management and control of Non-Communicable Diseases (NCDs) | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 7,859.00 |  |  |  | √ | DHS | DA, GHS |
|  |  | - Create efficient management, control and elimination of Neglected Tropical Disease (NTDs) Preparedness Team | Abamkrom, Adeiso,Asikasu, Asuokaw,Mepom, Nyanoa, Okurase O’ Darmang |  |  |  |  | 9,100.00 |  |  |  | √ | DHS | DA, GHS |
| Health Delivery | Births & Deaths Registration | - Registration of Births and Deaths | District wide |  |  |  |  |  |  | 1,600.00 |  | √ | DB&D | DHS, DA, AMs, UCMs |
|  |  | - Organize community sensitization on births and deaths registration | District wide |  |  |  |  |  |  | 1,200.00 |  |  |  |  |
| Health Delivery | Health Infrastructural Delivery) | - Completion of 1No. Female Ward | Adeiso Health Center |  |  |  |  | 391,438.96 |  |  |  | √ | DHS | DWD, DA, DPCU |
|  |  | - Completion of 4No. CHPS Compound | Katayensua, Okurase, Atimatim, Sukrong Cannan |  |  |  |  | 341,073.76 |  |  |  | √ | DHS | DWD, DA, DPCU |
|  |  | - Rehabilitation of 1No. CHPS Compound | Danso |  |  |  |  | 60,000.00 |  |  | √ |  | DHS | DWD, DA, DPCU |
|  |  | - Construction of 1No. CHPS Compound | Afabeng |  |  |  |  |  |  | 300,000.00 | √ |  | DHS | IPEP, DPs, DWD, DA |
|  |  | - Construction of 1No. 4-units Chamber & Hall Nurses’ Quarters | Owurakessim |  |  |  |  | 200,000.00 |  |  | √ |  | DHS | IPEP, DPs, DWD, DA |
|  |  | - Construction of 1No. District Hospital | Obeng Yaw |  |  |  |  | 80,000.00 |  |  | √ |  | OoP | DA, TAs, DWD, DPCU |
| Focus Area: Water and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Safe water delivery | Provision of water facilities | - Construction of 4No. Boreholes | Kyerenyame/Kumitse, Kofi Asare, Abisim, Ampofo |  |  |  |  | 80,000.00 |  |  | √ |  | DWD | IPEP, DPs, DA, DPCU, DWST |
|  |  | - Construction of 3No. Mechanized Boreholes | Tiokrom, Abetiase, Krodua-Ayigbetown |  |  |  |  | 135,000.00 |  |  | √ |  | DWD | MP, DPs, DA, DWST, DPCU |
|  |  | - Rehabilitation of 5No. Boreholes | Sukrong Budu, Abode, Guluba. Essaso, Kofi-Kyere |  |  |  |  | 40,000.00 |  |  | √ |  | DWD | MP, DPs, DA, DWST, DPCU |
|  |  | - Mechanization of 2No. Existing Boreholes | Kwamoako, Obeng Yaw |  |  |  |  | 30,000.00 |  |  | √ |  | DWD | DPs, DA, DWST, DPCU |
|  |  | - Extension of water from Small Town Pipe Water System in 1No. major town. | Adeiso |  |  |  |  |  | 20,000.00 | 30,000.00 | √ |  | DWD | DPs, WSMT, DA, AC/AMs |
|  | Capacity Building of WSMTs and DWST | - Formation, training and monitoring of 20No. Water Management Teams and DWST | Selected communities |  |  |  |  | 10,000.00 |  | 10,000.00 | √ |  | DWD | DA, DWST, DPCU, AM |
| Sanitation Improvement (Social Services Delivery) | Solid Waste Management (Health Delivery) | - Evacuation of 3No. refuse dumps | Asuokaw Zongo, Sukrong Bethlehem, Gyampo |  |  |  |  | 135,000.00 | 15,000.00 |  | √ |  | DEHSU | DHS, DPCU ACs/UCM/AM |
|  |  | - Provision of 5No. Skip refuse containers | Maame Dede , Breman, Danso, Sukrong Bethlehem, Asuokaw Zongo |  |  |  |  | 42,500.00 |  |  | √ |  | DEHSU | DPCU, ZoomLion, PPD |
|  |  | - Procure new landfill site for final waste disposal | Selected area |  |  |  |  |  | 30,000.00 |  | √ |  | DEHSU | DA, DWD, PPD, NADMO, ACs/UCM,AM, ZoomLion |
|  |  | - Purchase of sanitary tools and equipment | UWADA-DESHU |  |  |  |  | 20,000.00 |  |  | √ |  | DEHSU | DA, PrU |
| Sanitation Improvement | Household Toilet Promotion | - Support for 100No. household toilet construction | District-wide |  |  |  |  | 250,000.00 |  | 250,000.00 | √ |  | DEHSU | DWD, PPD, ACs/UCM,AM, Beneficiaries |
|  |  | - Organize public education and community sensitization on household toilet construction | District ide |  |  |  |  |  | 8,000.00 |  | √ |  | DEHSU | DHS, DA, ISD, PPD, NADMO, ACs/UCM,AM |
|  |  | - Rehabilitation of 2No. Public toilets | Mepom, Ndoda |  |  |  |  |  | 40,000.00 |  | √ |  | DEHSU | DWD, PPD, ACs/UCM,AM |
| Sanitation Improvement (Social Services Delivery) | Food and Water Hygiene Promotion | - Rehabilitation of 2No. meat shops | Adeiso and Mepom |  |  |  |  |  | 20,000.00 |  | √ |  | DEHSU | DWD, DHS, ACs/UCM/AM, |
|  |  | - Organize medical screening for food and drink handlers/vendors | District wide |  |  |  |  |  | 10,000.00 |  | √ |  | DEHSU | DHS, DA, ISD, ACs/UCM,AM |
|  |  | - Organize public education on food safety | District wide |  |  |  |  | 5,000.00 |  |  | √ |  | DEHSU | DHS, DA, ISD, ACs/UCM,AM |
| Sanitation Improvement (Social Services Delivery) | School Health and Sanitation Promotion | - Organize school health education programmes in 8 schools | Selected schools |  |  |  |  | 10,000.00 |  |  | √ |  | DEHSU | DoE, DHS, DA, ISD, ACs/UCM,AM |
|  |  | - Construction of 2No. 6-units KVIP for Basic schools | Atimatim DA, Kuntu D/A |  |  |  |  | 180,000.00 |  |  | √ |  | DWD | DEHSU, DoE, PPD |
| Sanitation Improvement (Social Services Delivery) | Environmental Health Promotion and Education Campaign | - Organize communal labour and clean-up exercises | District wide |  |  |  |  | 20,000.00 | 10,000.00 |  | √ |  | DEHSU | DA, ISD, ACs/UCM,AM, NADMO, ZoomLion |
|  |  | - Undertake registration and control of noxious and offensive trades | District wide |  |  |  |  |  | 10,000.00 |  | √ |  | DEHSU | DA, DBU,DFD, ACs/UCM,AM |
|  |  | - Construction of 1No. animal pound | Mepom |  |  |  |  |  | 60,000.00 |  | √ |  | DEHSU | DWD, TAs, PPD, ACs/UCM,AM |
| Focus Area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child Protection and Development (Social Welfare & Community Dev’t) | - Settle 70 cases on child maintenance family welfare, child custody and do follow-ups | Adeiso District Office and clients’ homes |  |  |  |  | 1,089.00 | 66.00 | 800 | √ |  | DSWCD | Client’s Family, AM/UCM, PS, District Court |
|  |  | - Inspect and register 25 Private day care centres and 5 NGOs | District Wide |  |  |  |  | 1,000 | 500 | 500 | √ |  | DSWCD | GES, AM/UCM, APS |
|  |  | - Sensitize 30 communities on Child Protection and other Human Rights issues | 30 selected communities |  |  |  |  | 1,600 | 1,000 | 1,400 | √ |  | DSWCD | GES, GHS, NCCE, AM/UCM, Traditional Authorities |
| Focus Area: Social Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Protection (Social Welfare and Community Development) | - Registration of 600 vulnerable persons | District Wide |  |  |  |  | 1,500 | 400 | 600 |  | √ | DSWCD | AM, UCM, GHS, GES, APS |
|  |  | - Link 800 vulnerable persons on LEAP, Free NHIS registration and other social protection interventions | District Wide |  |  |  |  | 600 | 200 | 400 |  | √ | DSWCD | NHIA, GHS, CFP, LEAP Secretariat |
| Focus Area: Disability-Inclusive Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Disability-Inclusive Development (Social Welfare and Community Development) | - Support 120 PWDs in business and other programs with PWD fund | District Wide |  |  |  |  |  |  | 250,000 |  | √ | DSWCD | Rural Banks, GDF,PWD’s Family, NBSSI |
|  |  | - Develop and coordinate community-based rehabilitation programmes for 30 PWDs | District Wide |  |  |  |  | 500.00 |  | 2,500.00 | √ |  | DSWCD | PWD’s Family, NGOs, CBOs, GDF, |
| Focus Area: Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Equality (Social Welfare and Community Development) | - Educate 30 families on the negative effects of Gender- Based Violence /Domestic abuse | District Office, selected communities |  |  |  |  | 1,300.00 | 400.00 | 1,000.00 | √ |  | DSWCD | AS/UCM, PS, District, Client’s Family |
|  |  | - Facilitate access to soft loan/grant from financial/government institutions for 4 economic gender-based groups. | District.-wide |  |  |  |  | 2,700.00 | 1,000.00 | 1,700.00 | √ |  | DSWCD | Rural Banks, NBSSI 1D1F Secretariat |
|  |  | - Formation of 2no. new women’s groups | District.-wide |  |  |  |  | 800.00 | 700.00 | 600.00 | √ |  | DSWCD | AM/UCM, NBSSI |
|  |  | - Organize demonstration work for 3no. women’s groups on vocational skills | District.-wide |  |  |  |  | 1,400.00 | 800.00 | 800.00 | √ |  | DSWCD | AM/UCM, NBSSI |
|  |  | - Under take 80 home visits | District wide |  |  |  |  | 1,655.00 | 0.00 | 100.00 | √ |  | DSWCD | AM, UCM, TAs |
| Focus Area: Youth Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Youth Development | Youth empowerment | - Provide support for 50 youths in employable skills apprenticeship training program | District-wide |  |  |  |  | 50,000.00 |  |  | √ |  | YEA | DA, MP, DPCU, AMs, ACs |
| Youth Development | Youth empowerment | - Regular update of YEA website with labour market information for the youth | UWADA-YEA |  |  |  |  | 1,000.00 |  |  |  | √ | YEA | MELR, GEA, Private Labour, AGI, Youth Groups |
| Youth Development | Youth empowerment | - Advocate for statistics on youth unemployment | District Wide |  |  |  |  |  |  | 5,000.00 |  | √ | YEA | District Statistician, GSS, YG |
|  |  | - Provide guidance & counselling Services on Career Development | District Wide |  |  |  |  |  |  | 5,000.00 |  | √ | YEA | Career Dev’t, Organization (Private sector), GES, YG |
| Youth Development | Youth in Agriculture | - Facilitate the formation of youth farmer-based organizations | District Wide |  |  |  |  |  |  | 4,000.00 | √ |  | YEA | DA, Agric Department, District,FBO, Youth Groups, NGOs |
| Youth Development | Youth empowerment | - Organise Capacity building sessions in entrepreneurship for the youth | District Wide |  |  |  |  |  |  | 10,000.00 | √ |  | YEA | Ghana Enterprises Agency/REP |
| Youth Development | Youth empowerment | - Establish Youth, Jobs and Enterprises Development Fund (YJEDE) to offer start-up capital to youth oriented businesses | District Wide |  |  |  |  |  |  | 50,000.00 | √ |  | YEA | Ghana Enterprises Agency, MASLOC |
| Youth Development | Youth empowerment | - Provide food, clothing, shelter and relocation to vulnerable youth | District Wide |  |  |  |  | 9,000.00 |  |  |  | √ | YEA | DSWCD, FPD, NADMO, NGOs |
| Focus Area: Employment and Decent Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Youth Development | Job Creation | - Facilitate the establishment of 1No. Cassava Processing factory | Adeiso |  |  |  |  | 20,000.00 |  |  | √ |  | DPU | DoA, DA, TAs, DPCU, Farmers, 1D1F Secretariat |
| Focus Area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Youth Development | Sports development | - Construction of 1No. AstroTurf sports stadium | Adeiso |  |  |  |  | 5,000.00 |  |  |  | √ | GNPC | MoS, TA, DA, YEA |
| Youth Development | Sports development | - Organize annual mass youth sports in the District | District Wide |  |  |  |  |  |  | 5,000.00 | √ |  | YEA | Youth Groups, NGOs DFA |
| Infrastructure Delivery and Mgt | Recreation and Leisure | - Construction of 2No. Community centres/ durbar grounds | Okaikrom, Nkyekyerekye |  |  |  |  | 180,000.00 |  |  | √ |  | DWD | MP, IPEP, DA, DPCU |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deforestation, Desertification and Soil Erosion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Deforestation, Desertification and Soil Erosion | - Reclamation of sand-winning sites | District wide |  |  |  |  |  |  | 100,000.00 | √ |  | DEHSU | NADMO, PPD, DoA, TAs, DWD, DPCU ACs/UCM/AM, |
|  |  | - Supervision and monitoring of sand-winning activities | District wide |  |  |  |  |  | 10,000.00 |  | √ |  | NADMO | DEHSU, PPD, DWD, DPCU, TAs. Landowners, Sandwinners |
| Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Climate Variability and Change | - Planting of 2000 trees/tree crops at sand-winned sites | District wide |  |  |  |  | 5,000.00 |  | 30,000.00 | √ |  | NADMO | DEHSU, PPD, DWD, DPCU, TAs. Landowners, Sandwinners |
| Focus Area: Transportation: Air, Rail, Water and Road |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Road infrastructure (Infrastructure development) | - Completion of 30m diameter and 900m of 0.6m line drain | Mepom |  |  |  |  | 338,000.00 |  |  |  |  | DWD | DA, PPD, NADMO, AC, AMs |
|  |  | - Completion of 1No. 48m span footbridge on River Asuogya | Adeiso Asuogya |  |  |  |  | 288,400.00 |  |  |  | √ | DWD | DA, PPD, NADMO |
|  |  | - Creation of 25km length of new access/link roads | Nkonkor No.1 – Nkonkor No.3, Katayensua – Adiembra No.2 |  |  |  |  | 100,000.00 | 20,000.00 |  | √ |  | DWD | DFR, PPD, DA, TAs, ACs/AM |
| Infrastructure Delivery and Management | Road infrastructure (Infrastructure development) | - Reshaping of 45km length of feeder roads | Obobese - Kwasi Nyarko, Maame Dede Junction-Israel, Nyanoah - Essaso - Timber junction, and Essaso - Brekum – Asaman, Apesika, Babytse, Ahwerease, Aboyensu, |  |  |  |  | 100,000.00 | 50,000.00 | 200,000.00 | √ |  | DWD | DFR, PPD, DA, TAs, ACs/AM |
| Infrastructure Delivery and Management | Road infrastructure (Infrastructure development) | - Facilitate the construction of Speed ramps & roads signs on Highway | Mepom, Sukrong Bethlehem Asikasu, Asuokaw, Okurase, |  |  |  |  | 10,000.00 |  |  | √ |  | DWD | GHA, MoT, DA, DPCU |
| Energy and Petroleum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Rural Electrification | - Facilitate the connection of 10 communities to the national grid | Ansah, Boateng, Abisim, Kumikye, Prempeh, Adukojo/Ade, Obobese, Amodeum, Ahwereasefom, Garuwa/lapor |  |  |  |  | 200,000.00 |  | 300,000.00 | √ |  | DWD | MP, DA, ECG, DPCU,MoEn |
| Infrastructure Delivery and Mgtt | Road infrastructure | - Provision and installation of 100No. streetlight bulbs | District wide |  |  |  |  | 200,000.00 |  |  | √ |  | DWD | DA, MLGDRD, DPCU, MP |
| Human Settlements Development and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Spatial Planning | - Organize public education/ sensitization on building regulations | Domponaise Junction and Asikasu |  |  |  |  | 4,000.00 |  |  |  | √ | PPD | DWD/NADMONCCE/ISD,AM Opinion leaders |
| Environmental Management | Street naming and property addressing | - Organize street naming and property addressing system | Adeiso |  |  |  |  | 50,000.00 |  |  |  | √ | PPD | DWD/ISD, SNPA AM, and Opinion Leaders |
| Environmental Management | Spatial Planning | - Preparation of local Planning Schemes for Communities | Domponaise Junction and Asikasu |  |  |  |  | 5,000.00 |  |  |  | √ | PPD | SNPA, AMand Opinion Leaders |
| Environmental Management | Spatial Planning | - Organize Technical Sub Committee Meetings | UWADA |  |  |  |  |  | 8,000.00 |  |  | √ | PPD | Committee members |
|  |  | - Purchase of E-PERMIT software Application | UWADA |  |  |  |  | 30,000.00 |  |  | √ |  | PPD | DA, DPCU, DWD, TCPD |
| Environmental Management | Spatial Planning | - Preparation of district Spatial Development Framework and Structure Plan | District wide |  |  |  |  | 100,000.00 | 50,000.00 |  | √ |  | PPD | DA, DPCU, DWD, LUPSA |
| Environmental Management | Spatial Planning (Disaster Prevention and Mgt) | - Organize Site inspections on all physical structures/development | District wide |  |  |  |  |  | 2,000.00 |  |  | √ | PPD | DWD, NADMO, GNFS, DA, AM, |
|  |  | - Registration of District Assembly lands | District Wide |  |  |  |  | 50,000.00 | 50,000.00 |  | √ |  | PPD | DA, Lands Commission, TAs, AMs, ACs |
| Focus Area: Drainage and Flood Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Road infrastructure | - Construction of 2No. Culverts | Asuaso, Babytse |  |  |  |  | 300,000.00 |  |  | √ |  | DWD | MP, DA, NADMO, DPCU |
|  |  | - Construction of 2No. Footbridges | Krodua-Ayigbetown, Sukrong Bethlehem |  |  |  |  |  |  | 200,000.00 | √ |  | DWD | IPEP, DA, NADMO, DPCU |
| Focus Area: Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical Development Control | - Supervision of all on-going DA projects | District wide |  |  |  |  |  | 5,000.00 |  |  | √ | DWD | DA, ACs, DoE, DHD, DFR, GETFUND |
|  | Physical Development Control | - Organize extensive development control activities | District wide |  |  |  |  |  | 5,000.00 |  |  | √ | DWD | PPD, WSC, DA, ACs, SPC, |
|  | Infrastructural Maintenance (Infrastructure development) | - Implementation of O&M Plan | District wide |  |  |  |  | 250,000.00 | 50,000.00 |  | √ |  | DWD | PPD, WSC, DA, ACs, DPCU, HoDs |
| Focus Area: Land Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Management | Disaster Prevention and management | - Sensitization of landowners and sand-winning Contractors on environmental degradation impacts | District-wide |  |  |  |  |  | 4,000.00 |  | √ |  | NADMO | DEHSU, PPD, DWD, DPCU, TAs. Landowners, Sandwinners |
| GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Local Governance and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | General Administration | - Organize all statutory meeting | UWADA Conference Hall |  |  |  |  |  | 79,000.00 |  |  | √ | Central Adminstration | DoE |
|  |  | - Promulgation of the Assembly’s Bye Laws | District wide |  |  |  |  | 30,000.00 |  |  |  | √ | Central Adminstration |  |
|  |  | - Procurement of 1No. office vehicle | UWADA |  |  |  |  | 200,000.00 |  |  | √ |  | CAD | TO, PrO, DPCU, DA |
|  |  | - Servicing and maintenance of vehicles and motorbikes | UWADA |  |  |  |  | 35,000.00 |  |  | √ |  | CAD | TO, PrO, DPCU, DA, all Depts |
|  |  | - Construction of 2No. 2-bedroom semi detach staff quarters | Adeiso |  |  |  |  | 550,000.00 |  |  | √ |  | DWD | DA, AMs, PPD, DPCU, TAs, |
| Management and Administration | General Administration | - Construction of vehicle parking lot | UWADA Office Adeiso |  |  |  |  | 60,000.00 |  |  | √ |  | DWD | PPD, DA,DPCU |
| Management and administration | Capacity building (Human Resource Mgt) | - Organize capacity building workshop for Hon. Assembly members and Area Council Members | UWADA |  |  |  |  | 15,000.00 |  |  | √ |  | HR | DA, DPCU |
| Management and administration | Capacity building (Human Resource Management) | - Prepare IGF Salary and validate established staff | UWADA |  |  |  |  |  | 2,400.00 |  |  |  | HR | DA, DPCU |
|  |  | - Update HRMIS data and submit reports. | UWADA |  |  |  |  | 2,400.00 |  |  | √ |  | HR | DA |
|  |  | - Organize capacity building for staff | UWADA |  |  |  |  | 25,000.00 |  |  | √ |  | HR | DA |
| Management and administration | Capacity building (Human Resource Management) | - Procure Office Equipment (1Tablet, 5Laptop and 5 desktop Computers, 5UPS 3printers, 2Scanners, 1Photocopier) | UWADA |  |  |  |  | 62,810.00 |  |  | √ |  | CAD | PrU, DA, HR |
| Management and administration | Capacity building (Human Resource Management) | - Procure Office Stationary | UWADA |  |  |  |  | 50,000.00 |  |  | √ |  | CAD | PrU, DA, HR |
|  |  | - Procure office furniture (Tables and swivel chairs) | UWADA |  |  |  |  | 50,000.00 |  |  | √ |  | CAD | PrU, DA, HR |
|  |  | - Procure office appliances (Air Conditioners, TV, Refrigerators and ceiling fans | UWADA |  |  |  |  | 70,000.00 |  |  | √ |  | CAD | PrU, DA, HR |
| Management and Administration | Finance and Revenue Mobilization | - Capacity Building Training and review meetings for all Collectors and revenue Mobilization unit | Adeiso |  |  |  |  |  | 14,400.00 |  | √ |  | DFO | DBU, DP, HR,DPCU |
| Management and Admin. | Finance and Revenue Mobilization | - Sensitization of major communities on payment of Rates | District-Wide |  |  |  |  |  | 12,000.00 |  |  | √ | DFO | DBU, DIO, DPCU,NCCE |
| Management and Admin. | Finance and Revenue Mobilization | - Operationalization of 3no. revenue centres | Kwasi Nyarko, Asuokaw and Nyanoa |  |  |  |  |  | 7,000.00 |  | √ |  | DFD | DBO, DIA, DPCU, DWE |
| Management and Administration | Finance and Revenue Mobilization | - Monitoring of Revenue Collection Centres and Check Points | Adeiso Market, Kwasi Nyarko, Asuokaw and Nyanoa |  |  |  |  |  | 10,000.00 |  |  | √ | DFD | DBO,DIA DPCU |
| Management and Administration | Finance and Revenue Mobilization | - Submission of monthly, quarterly and yearly returns to appropriate offices within stipulated time | Koforidua, Accra and Asamankese |  |  |  |  |  | 5,000.00 |  |  | √ | DFO | DIA, DA |
| Management and Admin. | Finance and Revenue Mobilization | - Preparation and auditing of end of year financial statement | Adeiso |  |  |  |  |  |  | 20,000.00 | √ |  | DFO | DIA, DA |
| Management and Administration | Finance and Revenue Mobilization | - Organize stakeholders consultative meeting on internal revenue generation improvement | District Wide |  |  |  |  | 5,000.00 | 5,000.00 |  | √ |  | CAD | DBU, Budget Committee, DPCU, F&A, Management |
| Management and Admin. | Finance and Revenue Mobilization | - Organize revenue sensitization programmes | District Wide |  |  |  |  |  | 8,000.00 |  | √ |  | CAD | DBU, Budget Committee, F & A, Finance Department |
| Management and Administration | Planning, Budgeting and Coordination | - Update socio-economic data on businesses and properties | District Wide |  |  |  |  | 10,000.00 | 5,000.00 |  | √ |  | CAD | DBU, Budget Committee, Finance Department |
| Focus Area: Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Popular Participation (Mgt and Administration | Public Accountability (Planning, Budgeting and Coordination) | - Organize two major Town Hall meetings | Adeiso & Mepom |  |  |  |  | 10,000.00 | 5,000.00 |  | √ |  | CAD | DPCU, DCE, , HoDs, TAs, AMs, UCMs, |
|  |  | - Organize community engagement/dialogue meetings | District-wide |  |  |  |  | 2,600.00 | 2,000.00 | 2,000.00 | √ |  | CAD | DPCU, DCE, , HoDs, TAs, AMs, UCMs, Comm. Memb. |
|  |  | - Organize Time with My Assembly radio programme | TRU FM |  |  |  |  | 12,000.00 |  |  |  | √ | ISD | DA, all depts. of the Assembly |
| Management and Administration | Public Accountability (Legislative Oversights) | - Preparation of Strategic Internal Audit Annual Plan | UWADA |  |  |  |  | 10,000.00 |  |  | √ |  | CAD | DIA, Audit Committee |
|  |  | - Preparation and submission of Internal Audit Reports | UWADA |  |  |  |  | 2,000.00 |  |  | √ |  | CAD | DIA, Audit Committee |
| Focus Area: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Security | - Creation of 1No. Police post | Obeng Yaw |  |  |  |  |  |  | 50,000.00 | √ |  | Ghana Police Service | DA, MP, PPD, NADMO, DPCU, TAs |
|  |  | - Formation and training of 5No. Community Watch Dogs in | Dziko-Nkwanta, Odeng, Obeng Yaw, Kpanikrom, Asukyereman |  |  |  |  | 2,000.00 |  | 2,000.00 | √ |  | Ghana Police Service | DA, MP, AM, NADMO, AC, DPCU, TAs, |
|  |  | - Establish 1No. District Fire Service Station | Adeiso |  |  |  |  | 50,000.00 |  |  | √ |  | GNFS | DA, NADMO, PPD |
| Focus Area: Corruption And Economic Crimes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | - Implementation and reporting on NACAP Plan | District-wide |  |  |  |  | 5,000.00 |  |  |  | √ | DPU | All depts. & agencies |
| Focus Area: Civil Society, and Civic Engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Popular Participation | Public Accountability | - Disseminate information on Government and DA policies, plans and projects | District wide |  |  |  |  | 20,000.00 |  |  |  | √ | ISD | NCCE, DA, DPCU, RISD, |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Hydrometeorological Threats |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster prevention and Management | - Organize community clean-up exercises | All Zones |  |  |  |  | 5,000.00 |  |  | √ |  | NADMO | Zoomlion |
| Environmental and Sanitation Management | Disaster prevention and Management | - Community sensitization on fire prevention | Kwasi Nyarko, Kofi-kyere, Domponease, Atimatim, Darmang |  |  |  |  | 3,500.00 |  |  | √ |  | NADMO | GNFS |
|  |  | - Formation of DVGs | Asuaba, Okurase, Owurakesim, Sukrong Budu, , |  |  |  |  | 4,000.00 |  |  | √ |  | NADMO | Police, GNFS, ISD |
|  |  | - Celebration of IDDR | Asuokaw Odumase |  |  |  |  | 10,000.00 |  |  |  | √ | NADMO | ALL DEPARMENTS |
|  |  | - Identification and field assessment of hazardous areas | All Zones |  |  |  |  | 5,000.00 |  |  | √ |  | NADMO | Hon. Assembly Members |
|  |  | - Procure and distribute relief items to disaster victims | District wide |  |  |  |  | 50,000.00 |  |  | √ |  | NADMO | DA |
| Focus Area: Covid-19 Response |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health Delivery (Social Services Delivery) | Covid-19 Response Health Delivery | - Establish effective and efficient Outbreak Preparedness Plan and Response Team for proactive interventions | District Health Directorate, Adeiso |  |  |  |  | 8,147.00 |  |  |  | √ | DHS | DA, GHS |
| IMPLEMENTATION COORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus Area: Implementation and Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | - Organize quarterly DPCU and Budget Committee meetings | DA Conference Hall |  |  |  |  | 23,400.00 |  |  | √ |  | CAD | DPU/ DBU DPCU/ Budget C’ttee DCE |
| Management and Administration | Planning, Budgeting and Coordination | - Preparation and submission of 2023 Composite AAP and Budget | DPU&DBU E.R.C.C/ N.D.P.C/MoF |  |  |  |  | 28,100.00 |  |  | √ |  | CAD | DPU, DBU, BC, DPCU, HoDs, DPSC, ERCC, NDPC, F&ASC |
| Management and Admin. | Planning, Budgeting and Coordination | - Organize Mid-year and End of year 2022 AAP review meetings | DA Conference Hall |  |  |  |  | 4,980.00 |  |  | √ |  | CAD | DPU,DPCUHoDs & Agencies, DPSC, DCE |
| Focus Area: Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Monitoring and Evaluation (Planning, Budgeting and Coordination) | - Organize quarterly 2022 M&E field exercises and meetings | District-wide & DA Conference Hall |  |  |  |  | 26,000.00 | 8,400.00 |  | √ |  | CAD | DPU, DPCU, DCE, HoDs, TAs, AMs, UCMs, ACs |
|  |  | - Preparation and submission of 2022 quarterly and annual Progress Reports, budget implementation report and monthly trend analysis for IGF | DPU & E.R.C.C/ N.D.P.C |  |  |  |  | 2,490.00 | 2,800.00 |  | √ |  | CAD | DPU, DPCU, HoDs, ERCC, NDPC |
| Focus Area: Production And Utilisation of Statistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Production And Utilisation of Statistics Planning, Budget and coordination | - Collection of data on Properties | Adeiso |  |  |  |  | 6,800.00 | 3,000.00 | 3,000.00 | √ |  | STATS | DFO/BUDGET/DPU |
|  |  | - Stakeholders workshop on statistical policies | UWADA |  |  |  |  |  | 4,000.00 |  | √ |  | STAT | D/A |
|  |  | - Establish and maintain a comprehensive statistical database | UWADA |  |  |  |  | 2,000.00 | 2,000.00 | 1,000.00 | √ |  | STATS | MIS |
|  |  |  |  |  |  |  |  | 8,441,059.80 | 689,666.00 | 5,040,700.00 |  |  |  |  |